## Introduction
RIBA Plan of Work 2020 - Toolbox v1.3
Last updated - February 2020
This Toolbox contains practical tools originally described in the RIBA Publication Assembling a Collaborative Project Team. It aligns with and supports the RIBA Plan of Work 2020, providing more detailed guidance, specific activities and focused tools that are essential for those responsible for and involved in assembling a project team. For more information on all of these publications please visit the website.
Watch the Toolbox Video
The commencement of a project is crucial because the decisions made by the client at that point in time, and the resultant initial appointments that are made, have a fundamental impact on how the project team will subsequently be assembled. This Toolbox contains practical tools that define WHO is in the project team? and WHAT does the project team need to do? This ensures that the best possible start to the project is achieved.
WHO is in the project team?
By carefully considering the roles that are required at each stage of a project and who is best placed to undertake them, along with the core decisions on how and when the contractor will be engaged, it is possible to prepare a Project Roles Table and a Contractual Tree. The Project Roles Table will outline all core project roles required and the parties responsible and the Contractual Tree will clarify the contractual relationships between these parties. The processes involved aim to ensure that these outputs are well thought-out and robust. This allows Schedules of Services, Information Exchanges and design responsibilities to be considered in greater detail.
Select one of these tools below:
Pick Lists » |  | Project Roles Table (PRT) » | Contractual Tree (CT) »
WHAT does the project team need to do?
Defining what the project team needs to do is a fundamental element in the assembly of a collaborative project team. Once the Design Responsibility Matrix incorporating Information Exchanges and Schedules of Services have been completed and all the documents agreed on, each member of the project team can be confident that design responsibility has been considered holistically and that they are all working towards the same client goals. More importantly, by considering these issues early on there is less likelihood of disagreements or disputes arising and the project team is more likely to be focused on the collaborative strategies which are necessary to drive the project forward. It is recommended that the Design Responsibility Matrix is prepared at Stage 1 to ensure each parties’ fees are based on agreed deliverables at each stage and on the areas of design that each party will be responsible for. The table allows the allocation of design duties between design team members and also to the specialist subcontractors via the Building Contract. The Schedules of Services ensure that tasks are allocated to a party set out in the Project Roles Table. Depending on the project, additional tasks may be added and not all Stages may be required.
Select one of these tools below:
Pick Lists » |  | Design Responsibility Matrix incorporating Information Exchanges (DRMIE) »
Select a Schedule of Services:
Stage 0: Strategic Definition (0 -SD)
Stage 1: Preparation and Briefing (1 - PB)
Stage 2: Concept Design (2 - CD)
Stage 3: Spatial Coordination (3- SC)
Stage 4: Technical Design (4 - TD)
Stage 5: Manufacturing and Construction (5 - MC)
Stage 6: Handover and Close Out (6 - H)
Stage 7: Use (7- U)
The Terms and Conditions for accessing and using RIBA guidance are outlined in the website below. By accessing or using this tool, you are indicating that you agree to be bound by these Terms and Conditions.
https://www.architecture.com/about/terms-of-use
Royal Institute of British Architects

## Setup - Pick Lists
Setup: Pick Lists
List of parties | Level of detail | Level of information | Yes / No | Guide to Pick Lists
[Not decided] | [Not decided] | [Not decided] | [Not decided]
[Not required] | [Not required] | [Not required] | Yes | Bold values
ABC Architects | 2 | 2 | No | Values in bold text represent suggested values, or those which will be consistent across 90% of projects. You are free to change these suggestions if you feel others may be more appropriate for your project.
Alpha Landscape | 3 | 3
Big Beam Ltd | 4 | 4
Big City Construction | 5 | 5 |  | List of parties
Clear Costs |  | 6 |  | Add the list of parties involved in the project to this pick list. It will be then used to help complete the various tools within this Toolbox.
Newtown CC
Wires and Fires |  |  |  | Level of design and Information exchange
Safety Ensured Ltd |  |  |  | The values in these pick lists are used in the Design Responsibilities and Information Exchange Matrix. Alternative pick list values could be either the type of specification (outline, performance, full…) and drawing scales (1:100, 1:10, 1:5…).
What is meant by level of detail, design and information exchange?
Although CAD or BIM information is produced ‘full size’, it is typically issued, or exchanged, as drawings in ‘hard’ (prints) or ‘soft’ (electronic) formats, with the level of detail added to the CAD model dictated by the scale of the output (i.e. 1:100, 1:50, 1:5, 1:1, etc.). BIM changes this approach as such outputs are no longer required (although it is likely that 2D ‘slices’ through a model will continue to be used as contractual documents for some time). The level of detail therefore progresses from an issue of scale to one of purpose.
For example, if the model is being used for design discussions with a client, one level of detail is required in the model, whereas a model being handed over to a specialist subcontractor (to develop the curtain walling, for example) requires a different level of detail. As this transitional subject is in an embryonic state, the Information Exchanges in the Design Responsibility Matrix are conceived in a manner that considers the output scale. Guidance on the appropriate digital level of detail is being developed and will be published in the future.
For more information about level of definition on the NBS BIM Toolkit website please see:
https://toolkit.thenbs.com/articles/levels-of-definition
Cell N40 = NBS 40 years
Note on B4: List of parties: Add the list of parties involved in project to this pick list. It will be then used to help complete the various tools within this Toolbox.
Note on C4: Level of design: The values in this pick list are used in theDesign Responsibilities Matrix incorporating Information Exchanges
Note on D4: Information exchange: The values in this pick list are used in the Design Responsibilities Matrix incorporating Information Exchanges
Note on E4: Yes or No: The values in this pick list are used in the Design Responsibilities and Information Exchange Matrix to determine answers to questions such as "Is a warranty required?".

## PRT
Project Roles Table
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Client
Client adviser
Project lead
Lead designer
Construction lead
Architect
Civil and structural engineer
Building services engineer
Cost consultant
Contract administrator
Health and safety advisor
Access consultant
Acoustic consultant
Archaeologist
BREEAM assessor
Cladding specialist
Catering consultant
Facilities management (FM) advisor
Fire engineer
Highways consultant
Information manager
Interior designer
Landscape architect
Lighting designer
Masterplanner
Operational lead
Party wall surveyor
Planning consultants
Security advisor
Signage designer
Sustainability advisor
Technical advisor
Other additional project role 1
Other additional project role 2
Note on B8: Client: The party commissioning the design and construction of a project. The client may be an individual or a company. In the latter case, an individual should act as a single point of responsibility for decision and communication even if numerous bodies, or individuals, within the client organisation will contribute to decisions. The client may use a RIBA Client Adviser, a specially accredited individual, able to provide strategic advice in the early stages of a project in relation to the strategic definition or briefing aspects as well as the best methods for setting up the project team.
Note on B9: Client Adviser: A consultant providing strategic or specialist advice particularly during the early project stages.
Note on B10: Project Lead: The party responsible for managing all aspects of the project and ensuring that the project is delivered in accordance with the Project Programme.
Note on B11: Lead designer: The party responsible for managing all aspects of the design, including the co-ordination of the design and the integration of specialist subcontractors’ design, where applicable, into the coordinated design.
Note on B12: Construction lead: The party responsible for constructing the project and for providing construction advice in the early stages. The contractor would be the construction lead at Stage 5. This role has been introduced to provide flexibility regarding who performs this role prior to work commencing on site.
Note on B13: Architect: Responsible for carrying out the architectural design.
Note on B14: Civil and structural engineer: Responsible for carrying out the structural engineering design. On larger projects civil engineering aspects would be undertaken by this role.
Note on B15: Building services engineer: Responsible for carrying out the building services design.
Note on B16: Cost consultant: The party responsible for producing Cost Information as the design progresses. This information will vary depending on the project but may include the overall Project Budget, estimates of the construction cost and life cycle cost analysis.
Note on B17: Contract administrator: The party responsible for the administration of the Building Contract, including issuing of additional instructions and the various certificates required to allow the handover and occupation of a building, until all of the defects have been rectified and the defect period concluded.
Note on B18: Health and safety advisor: Responsible for health and safety aspects as defined by legislation and in line with other project objectives and health and safety best practice.
Note on B19: Access consultant: Provides specialist advice in relation to disabled and other access issues.
Note on B20: Acoustic consultant: Provides specialist acoustic advice on particular projects in relation to sound quality in spaces or noise transfer between rooms or from the external environment.
Note on B21: Archaeologist: Undertakes desktop and site investigations to comply with any requirement of the planning consent.
Note on B22: BREEAM assessor: Carries out BREEAM assessments.
Note on B23: Cladding specialist: Undertakes specialist design and/or reviews of aspects of the external cladding of a building, particularly where bespoke solutions are proposed.
Note on B24: Catering consultant: Provides strategic and briefing catering advice as well as specific designs derived from the final catering brief.
Note on B25: Facilities management (FM) advisor: Reviews the design proposals and comments on facilities management and in-use maintenance matters.
Note on B26: Fire engineer: Provides fire engineering advice in relation to fire engineered solutions or advice in relation to fire aspects of the Building Regulations.
Note on B27: Highways consultant: Provides strategic advice on the implications of a design on the adjacent road network and may provide travel plans, transport assessments or other roadrelated information.
Note on B28: Information manager: Manages the flow of information between parties – note that this is not a design role.
Note on B29: Interior designer: Provides particular design services in relation to the interior design of a project.
Note on B30: Landscape architect: Responsible for carrying out the landscape design.
Note on B31: Lighting designer: Provides specialist lighting advice internally or in relation to the floodlighting and external lighting of a project.
Note on B32: Masterplanner: Provides specialist advice for larger sites in relation to planning, roads, social issues and other high-level strategies.
Note on B33: Operational lead: Responsible for the facilities management (FM) aspects of the building.
Note on B34: Party wall surveyor: Provides specialist advice in relation to adjacent properties and issues such as right of light.
Note on B35: Planning consultant: Provides specialist advice in relation to planning applications.
Note on B36: Security advisor: Considers security issues in relation to the design of a building.
Note on B37: Signage designer: Provides wayfinding strategies and the design of the corresponding signage.
Note on B38: Sustainability advisor: Provides strategic advice in relation to green issues.
Note on B39: Technical advisor: A consultant employed by the client to provide specific advice, particularly on design and build or contractor-led procurement routes.
Note on B40: Other additional project role 1: Add other additional project roles as required.
Note on B41: Other additional project role 2: Add other additional project roles as required.

## CT
Contractual Tree Example
All Stages
This worksheet gives a simple example from the RIBA Publication Assembling a Collaborative Project Team.
The preparation of the Contractual Tree can be undertaken when the Project Roles Table is being completed; the two are intrinsically linked. They have, however, been kept as two distinct activities due to the different outputs that are created. There can also be benefits in considering the project roles in isolation from contractual issues.
The Contractual Tree is prepared using the parties identified in the Project Roles Table. One Contractual Tree should be sufficient for the majority of projects, although where a design and build contract is utilised, a second Contractual Tree may be required to clarify any contractual changes (for example, novation), even though the parties involved may remain the same (as in the example below)...
Example 1: Large project Contractual Tree - Stages 1 -3
Example 2: Contractual Tree - Traditional Building Project
Notes
Note 1: Architect may undertake this role in certain circumstances
Note 2: Specialist practice may undertake this role is some instances
"Sam Wilson"
RIBA Client advisor
"Big Widget Ltd"
Client
"Architectural practice"
Lead designer
Architect
"Cost consultant practice"
Cost consultant
Contract administration
"Big City PM"
Project lead
Health and safety adviser
"Structural engineering practice"
Civil and structural engineer
"Building services practice"
Building services engineer
"Add Client Name"
Client
"Add Name"
Cost consultant
- note 1
"Add Name"
Building Services Engineer
"Add Name"
Structural Engineer
"Add Architect Practice Name"
Project Lead
Lead Designer
Architect
Construction Lead (stages 2+3)
Contract Administrator
Health and Safety Advisor - note 2
"Add Name"
Construction Lead (stages 4-6)

## DRMIE
Design Responsibility Matrix incorporating Information Exchanges
Guidance on selection of design objects (Tip: To hide this row right click on the row and select 'hide') |  | The aspects of design should be titled and coded using the Uniclass 2015 classification tables for objects such as spaces, elements, systems and products, as appropriate. These tables and a free online digital plan of work tool can be found on the NBS BIM Toolkit website [1]. Technical support articles are provided on on classification [2], and levels of definition [3]. Uniclass 2015 is aligned to ISO 12006-2 [4], and was in part funded by Innovate UK on behalf of the UK Government's BIM Task Group [5]). (All websites are listed in the 'Useful links' worksheet in this document)
|  | 2 - Concept Design |  |  | 3 - Spatial Coordination |  |  | 4- Technical Design |  |  | 4 - Technical Design
Aspect of design |  | Design team |  |  | Design team |  |  | Design team |  |  | Contractor |  |  | Building contractor
Classification | Title | Design responsibility | Level of detail (LOD) | Level of information (LOI) | Design responsibility | Level of detail (LOD) | Level of information (LOI) | Design responsibility | Level of detail (LOD) | Level of information (LOI) | Design responsibility | Level of detail (LOD) | Level of information (LOI) | Contractor's designed portion | Collateral Warranty required? | Notes
Ss_15 - EARTHWORKS
Ss_15_10_30 | Excavating and filling systems
Ss_15_30_50 | Masonry repair and renovation systems
Ss_15_30_90 | Timber repair and renovation systems
Ss_20 - STRUCTURAL SYSTEMS
Ss_20_05_15 | Concrete foundation systems
Ss_20_05_50 | Minor concrete substructure systems
Ss_20_05_65 | Piling systems
Ss_20_10_70 | Shelter systems
Ss_20_10_75 | Structural framing systems
Ss_25 - WALL AND BARRIER SYSTEMS
Ss_25_10_20 | Curtain walling systems
Ss_25_10_30 | Framed partition systems
Ss_25_10_32 | Framed wall structure systems
Ss_25_10_35 | Framed glazed systems
Ss_25_11_16 | Concrete wall systems
Ss_25_12_60 | Panel cubicle systems
Ss_25_12_65 | Panel partition systems
Ss_25_12_80 | Structural glass wall systems
Ss_25_13_33 | Glass wall systems
Ss_25_13_50 | Masonry wall systems
Ss_25_14_63 | Post, rail and board fence systems
Ss_25_14_67 | Post, wire and mesh fence systems
Ss_25_15_60 | Pedestrian safety barrier and guarding systems
Ss_25_16_94 | Vehicle restraint systems
Ss_25_20_08 | Board cladding systems
Ss_25_20_14 | Composite panel cladding systems
Ss_25_20_15 | Concrete cladding systems
Ss_25_20_33 | Glass fibre reinforced concrete (GRC) cladding systems
Ss_25_20_35 | Glass fibre reinforced plastics (GRP) cladding systems
Ss_25_20_50 | Metal sheet cladding systems
Ss_25_20_68 | Profiled sheet cladding systems
Ss_25_20_70 | Rainscreen cladding systems
Ss_25_20_72 | Sheet cladding systems
Ss_25_20_85 | Stone cladding systems
Ss_25_20_90 | Unit cladding systems
Ss_25_25_45 | Lining and casing systems
Ss_25_25_75 | Rigid sheet fine lining and panelling systems
Ss_25_25_85 | Stone lining systems
Ss_25_30_20 | Door, shutter and hatch systems
Ss_25_30_95 | Window systems
Ss_25_32_35 | Gate systems
Ss_25_36_95 | Vehicle access point control systems
Ss_25_38_20 | Door, window and gate hardware systems
Ss_25_45_02 | Acoustic covering systems
Ss_25_45_70 | Render and roughcast coating systems
Ss_25_45_72 | Rendered insulation systems
Ss_25_45_85 | Sprayed coating systems
Ss_25_45_88 | Tiling systems
Ss_25_50_45 | Louvre and shading systems
Ss_25_60_30 | Fire stopping systems
Ss_25_60_35 | Glazing systems
Ss_25_60_50 | Metal sheet wall flashing and weathering systems
Ss_30 - ROOF, FLOOR AND PAVING
Ss_30_10_30 | Framed roof structure systems
Ss_30_10_50 | Monolithic roof structure systems
Ss_30_10_90 | Unit roof structure systems
Ss_30_12_85 | Structural deck systems
Ss_30_14_05 | Asphalt road and paving systems
Ss_30_14_15 | Concrete road and paving systems
Ss_30_14_80 | Unbound aggregate paving systems
Ss_30_20_10 | Board floor systems
Ss_30_20_30 | External deck and boardwalk systems
Ss_30_20_70 | Raised floor systems
Ss_30_20_90 | Wood and composite unit flooring systems
Ss_30_20_95 | Wood strip and board fine flooring systems
Ss_30_25_10 | Board ceiling systems
Ss_30_25_22 | Demountable suspended ceiling systems
Ss_30_30_72 | Rooflight and window systems
Ss_30_30_73 | Roof ventilator systems
Ss_30_40_10 | Board roof covering systems
Ss_30_40_30 | Flat roof covering systems
Ss_30_40_34 | Glass roofing systems
Ss_30_40_50 | Metal sheet roof and dormer covering systems
Ss_30_40_55 | Metal composite panel roof covering systems
Ss_30_40_65 | Profiled sheet roof covering systems
Ss_30_40_95 | Unit roofing systems
Ss_30_42_10 | Calcium sulfate based screed systems
Ss_30_42_15 | Cementitious screed systems
Ss_30_42_30 | Floor paint systems
Ss_30_42_32 | Floor tiling systems
Ss_30_42_52 | Mastic asphalt flooring and floor underlay systems
Ss_30_42_54 | Monolithic flooring systems
Ss_30_42_72 | Resilient and textile floor covering systems
Ss_30_60_50 | Metal sheet roof flashing systems
Ss_30_75_50 | Metal sheet gutter lining systems
Ss_32 - DAMP-PROOFING, WATERPROOFING AND PLASTER FINISHING
Ss_32_20_20 | Damp-proof courses renewal and insertion systems
Ss_32_20_30 | Floor damp-proofing systems
Ss_32_20_95 | Wall damp-proofing systems
Ss_32_46_50 | Metal lathing and anchored mesh reinforcement systems
Ss_32_46_65 | Plaster coating systems
Ss_35 - STAIR AND RAMP SYSTEMS
Ss_35_10_25 | External stair and ramp systems
Ss_35_10_30 | Fixed utilitarian access systems
Ss_35_10_40 | Internal stair and ramp systems
Ss_35_10_85 | Structural stair and ramp systems
Ss_35_40_82 | Stair carpeting systems
Ss_37 - TUNNEL, SHAFT, VESSEL AND TOWER SYSTEMS
Ss_37_14_70 | Refuse and linen chute systems
Ss_37_16_65 | Pond and wetland systems
Ss_37_16_90 | Trench, pipeway and pit systems
Ss_40 - SIGNAGE, FITTINGS, FURNISHINGS AND EQUIPMENT SYSTEMS
Ss_40_10_25 | External signage and interpretation systems
Ss_40_10_30 | Fire and safety signage systems
Ss_40_10_40 | Internal architectural signage systems
Ss_40_15_25 | Catering FF&E systems
Ss_40_15_35 | General and joinery FF&E systems
Ss_40_15_46 | Laundry FF&E systems
Ss_40_15_75 | Sanitary appliance systems
Ss_40_15_90 | Toilet systems
Ss_40_20_30 | External public realm FF&E systems
Ss_40_30_85 | Static permanent access and safety equipment systems
Ss_40_90_40 | Intumescent systems
Ss_40_90_60 | Painting and clear finishing systems
Ss_40_90_95 | Wood preservative and fire retardant treatment systems
Ss_45 - FLORA AND FAUNA SYSTEMS
Ss_45_10_10 | Bird and vermin control systems
Ss_45_10_95 | Vegetation control systems
Ss_45_30_05 | Aquatic and wetland planting systems
Ss_45_35_05 | Amenity and ornamental planting systems
Ss_45_35_30 | Forestry, biomass, hedging and roadside planting systems
Ss_45_35_45 | Lawn and meadow planting systems
Ss_45_40_28 | External container planting systems
Ss_45_40_47 | Living roof systems
Ss_45_40_95 | Vertical planting systems
Ss_45_70_05 | Animal conservation systems
Ss_50 - DISPOSAL SYSTEMS
Ss_50_30_02 | Rainwater drainage systems
Ss_50_30_04 | Above ground waste water drainage systems
Ss_50_30_08 | Below ground gravity drainage systems
Ss_50_30_10 | Below ground pumped drainage systems
Ss_50_30_45 | Land drainage systems
Ss_50_30_65 | Pressure relief drainage systems
Ss_50_70_85 | Sustainable drainage systems (SuDS)
Ss_55 - PIPED SUPPLY SYSTEMS
Ss_55_20_34 | Gas supply systems
Ss_55_30_35 | Gaseous and foam fire extinguishing systems
Ss_55_30_65 | Portable fire extinguishing systems
Ss_55_30_96 | Water fire extinguishing systems
Ss_55_70_38 | Hot and cold water supply systems
Ss_55_70_42 | Irrigation systems
Ss_55_70_96 | Water feature systems
Ss_55_70_97 | Water reclamation systems
Ss_55_70_98 | Water treatment systems
Ss_60 - HEATING, COOLING AND REFRIGERATION SYSTEMS
Ss_60_40_15 | Combined heating, cooling and power
Ss_60_40_17 | Cooling systems
Ss_60_40_36 | Heat pump systems
Ss_60_40_37 | Heating systems
Ss_60_60_15 | Cold room systems
Ss_65 - VENTILATION AND AIR CONDITIONING SYSTEMS
Ss_65_40_33 | General space ventilation systems
Ss_65_40_80 | Smoke extract and control systems
Ss_65_40_94 | Vehicular space ventilation systems
Ss_65_80_05 | Central air conditioning systems
Ss_65_80_45 | Local air conditioning systems
Ss_70 - ELECTRICAL SYSTEMS
Ss_70_10_80 | Solar power generation systems
Ss_70_30_45 | Low-voltage systems
Ss_70_30_80 | Small power systems
Ss_70_80_25 | External lighting systems
Ss_70_80_33 | General space lighting systems
Ss_75 - COMMUNICATIONS, SECURITY, SAFETY, CONTROL AND PROTECTION
Ss_75_10_21 | Data distribution and telecommunications systems
Ss_75_10_46 | Listening systems
Ss_75_10_68 | Public communications systems
Ss_75_40_02 | Access control systems
Ss_75_40_53 | Monitoring systems
Ss_75_40_75 | Security detection alarm systems
Ss_75_50_11 | Call and alarm systems
Ss_75_50_28 | Detection and alarm systems
Ss_75_70_54 | Metering, monitoring and management systems
Ss_75_80_45 | Electrical protection systems
Ss_80 - TRANSPORT SYSTEMS
Ss_80_20_62 | People conveying systems
Ss_80_30_25 | Dynamic permanent access and safety equipment systems
Ss_80_50_60 | Passenger and goods lift systems
Note on R7: The Design Responsibility Matrix cannot deal with the complexity of the many design interfaces encountered on a project. To bring further clarity notes can be added to bring clarity on certain subjects.
Note on D10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on E10: Level of detail Levels of detail set out how much geometric information is required. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on F10: Level of information Levels of information define specification and data requirements. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on G10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on H10: Level of detail Levels of detail set out how much geometric information is required. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on I10: Level of information Levels of information define specification and data requirements. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on J10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on K10: Level of detail Levels of detail set out how much geometric information is required. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on L10: Level of information Levels of information define specification and data requirements. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on M10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on N10: Level of detail Levels of detail set out how much geometric information is required. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on O10: Level of information Levels of information define specification and data requirements. For further information please see: - https://toolkit.thenbs.com/articles/levels-of-definition
Note on P10: Contractor's designed portion: This column is for use on a JCT traditional form of contract using the Contractor’s Designed Portion to allocate discrete aspects of the design to the contractor within the Building Contract. It can be deleted for design and build or contractor-led forms of procurement.
Note on Q10: Collateral Warranty required? This column is for use on larger projects to allow aspects of the design where the client may require a Collateral Warranty to be provided by a specialist subcontractor to be identified and incorporated into the Building Contract.
Note on R10: Notes: The Design Responsibility Matrix cannot deal with the complexity of the many design interfaces encountered on a project. To bring further clarity, notes can be added on certain subjects.

## 0 - SD
Multidisciplinary Schedule of Services
0 - Strategic Definition
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 1 - PB
Multidisciplinary Schedule of Services
1 - Preparation and Brief
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 2 - CD
Multidisciplinary Schedule of Services
2 - Concept Design
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 3 - SC
Multidisciplinary Schedule of Services
3 - Spatial Coordination
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 4 - TD
Multidisciplinary Schedule of Services
4 - Technical Design
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 5 - MC
Multidisciplinary Schedule of Services
5 - Manufacturing and Construction
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 6 - H
Multidisciplinary Schedule of Services
6 - Handover
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles

## 7 - U
Multidisciplinary Schedule of Services
7 - Use
Project role | Party | Tasks to be undertaken
All roles
Client and/or Client Advisor | 0
Project Lead | 0
Lead Designer | 0
Architect | 0
Building Services Engineer | 0
Civil & Structural Engineer | 0
Cost Consultant | 0
Construction Lead | 0
Contract Administrator | 0
Health & Safety Advisor | 0
All additional project roles
Notes: Services required as part of on-going (long term) stage 7 duties are not list. It is anticipated that this will be included in separate professional services contracts or operating contracts.

## Useful links
Useful links
1 | NBS BIM Toolkit | https://toolkit.thenbs.com/
2 | Technical article on classification | https://toolkit.thenbs.com/articles/classification
3 | Technical article on levels of definition | https://toolkit.thenbs.com/articles/levels-of-definition
4 | ISO 12006-2 | http://www.thenbs.com/publicationindex/DocumentSummary.aspx?PubID=76&DocID=285902
5 | Official BIM Level 2 website | http://bim-level2.org/